U.S. Department of Education

Grant Performance Report (ED 524B)

Project Status Chart

PR/Award # (11 characters): H328M150099

SECTION A - Performance Objectives Information and Related Performance Measures Data (See Instructions.  Use as many pages as necessary.)

# 1. Project Objective 	[  ]  Check if this is a status update for the previous budget period.

# Increase parents’ knowledge of IDEA, early intervention, response to intervention, and transition through the provision of trainings and workshops.

| 1.a. Performance Measure | Measure Type | Quantitative Data |
| --- | --- | --- |
| 25 trainings and workshops will be held, with a cumulative attendance of 500 families. | PROJECT |  |  |
|  |  | Raw Number | Ratio | % | Raw Number | Ratio | % |
|  |  | 500 |  |  | 521 |  |  |

| 1.b. Performance Measure | Measure Type | Quantitative Data |
| --- | --- | --- |
| 20 percent of all families attending trainings and workshops will be culturally and linguistically diverse. | PROJECT |  |  |
|  |  | Raw Number | Ratio | % | Raw Number | Ratio | % |
|  |  |  | 100/500 | 20 |  | 96/521 | 18 |

| 1c. Performance Measure | Measure Type | Quantitative Data |
| --- | --- | --- |
| The percentage of Parent Training Information Centers’ products and services deemed to be useful to improve educational and early intervention policy or practice by an independent review panel of experts qualified to review the substantive content of the products or services. | PROGRAM |  |  |
|  |  | Raw Number | Ratio | % | Raw Number | Ratio | % |
|  |  |  | 93/100 | 97 |  | 99/100 | 99 |

| 1.d. Performance Measure | Measure Type | Quantitative Data |
| --- | --- | --- |
| 85% of families who respond to a post-workshop surveys will indicate that they understand how they can use the information to address a concern by giving a rating of 2 or 3 on a 4-point Likert scale. | PROJECT |  |  |
|  |  | Raw Number | Ratio | % | Raw Number | Ratio | % |
|  |  |  | 85/100 | 85 |  | 334/363 | 92 |

| 1.e. Performance Measure | Measure Type | Quantitative Data |
| --- | --- | --- |
| The percentage of materials used by Parent Training and Information Centers projects deemed to be of high quality by an independent review panel of experts qualified to review the substantive content of the products or services. | PROGRAM | Target | Actual Performance Data |
|  |  | Raw Number | Ratio | % | Raw Number | Ratio | % |
|  |  |  | 93/100 | 93 |  | 99 / 100 | 99 |

| 1.f. Performance Measure | Measure Type | Quantitative Data |
| --- | --- | --- |
| 85% of families who respond to the Parent Program Measure Survey would recommend the parent center to friends and family. (N is number of respondents answering affirmatively and Y is number of responses. Z is the actual percentage.) | PROJECT | Target | Actual Performance Data |
|  |  | Raw Number | Ratio | % | Raw Number | Ratio | % |
|  |  |  | 85 /100 | 85 |  | 16/18 N/Y | 88 Z |

Explanation of Progress (Include Qualitative Data and Data Collection Information)

1a. – The numbers reported are tallies of our sign-in sheets for the 26 trainings and workshops we held.  Attendees were asked to identify themselves as parents, professionals, or community members.  In addition to the number of parents reported here, 102 professionals attended the trainings, and 31 community members.  Family members attending more than one training were counted for each training that they attended.  The most widely attended trainings continue to be “IEP Basics,” but participants have expressed that they want more training on transition to adult life.

1b. – The total cumulative number of culturally and diverse family members who attended trainings and workshops fell short of our goal of 100.  Family members attending multiple trainings were counted multiple times.  However, this represents an increase from previous reporting periods.  Included in the numbers were the 36 participants in three Spanish only and 10 participants in Cantonese only workshops on IDEA basics.  We attribute our increasing success to the work of our diverse staff, who personally invited many parents to attend, and the availability of both interpretation and childcare at our evening trainings in those communities.  One parent who attended with the help of an interpreter said, “I never knew that I could ask for an IEP meeting at any time.  Thank you for getting the information to me in a language I could understand.”

1d. – We provided evaluation sheets at all trainings, and received 363 back.  The target and actual figures represent responses to the question, “I understand how I can use the information I learned today to address a concern I have about my child.”  Participants responded using a 0-3 point Likert scale, where 0 represents “not at all” and 3 represents “very much.”  We accepted all responses of 2 or 3, a total of 338, as indicting that the respondents believed that they understood how to use the information.

1f. - Target and actual numbers were based on our parents’ response to the Parent Program Measure Survey of random service recipients.  We provided information to the CPIR from the 7 parents they required we report, but we surveyed a total of 18 parents. Of the 18 families who responded to our survey, 16 indicated that they would recommend our parent center to family and friends.  We followed up with the two families who would not recommend our services to see how we could improve.

U.S. Department of Education

Grant Performance Report (ED 524B)

Project Status Chart

PR/Award #  (11 characters): __ H328M140099__________

SECTION A - Performance Objectives Information and Related Performance Measures Data (See Instructions.  Use as many pages as necessary.)

# 2. Project Objective 	[  ]  Check if this is a status update for the previous budget period.

| 2.a. Performance Measure | Measure Type | Quantitative Data |
| --- | --- | --- |
|  |  | Target | Actual Performance Data |
|  |  | Raw Number | Ratio | % | Raw Number | Ratio | % |
|  |  |  | / |  |  | / |  |

| 2.b. Performance Measure | Measure Type | Quantitative Data |
| --- | --- | --- |
|  |  | Target | Actual Performance Data |
|  |  | Raw Number | Ratio | % | Raw Number | Ratio | % |
|  |  |  | / |  |  | / |  |

Explanation of Progress (Include Qualitative Data and Data Collection Information)

U.S. Department of Education

Grant Performance Report (ED 524B)

Project Status Chart

PR/Award # (11 characters): _ H328M140099 _____

SECTION B - Budget Information (See Instructions.  Use as many pages as necessary.)

If applicable, describe any significant changes to your budget resulting from modification of project activities.

If applicable, describe any changes to your budget that affected your ability to achieve your approve projects activities and/or project objectives.

If applicable, describe any changes in the budget that were approved by the Project Officer and date of approval.

If there are funds to be carried over to the next budget period, explain why, provide an estimate, and describe a plan to use the unexpended funds.

Optional:  You can submit a table showing actual expenditures.

Examples:

- We moved in May, 2016 and are paying higher rent because of the change.  In addition, our contractual costs have decreased because we hired a bookkeeper to take over major functions of our external accounting firm.  We requested a budget modification, and our Project Officer approved the modification in an email dated June 16, 2016.

- There have been no significant changes to our budget.  We do not anticipate any significant changes in the upcoming year.  We do not expect that there will be any changes to our project that will affect the budget in any way that would need pre-approval from the Department.

- We notified our Project Officer in April 2016 of our intention to include a de minimus indirect fate of 10%.  The project officer approved the change on April 20, 2016.

SECTION C - Additional Information (See Instructions.  Use as many pages as necessary.)

(Use this section to describe any relevant aspect of your project not covered elsewhere in the report, such as unanticipated outcomes or benefits from the project.)

Although our plan to provide trainings on response to intervention did not materialize, as a consequence of our first presentation in a school district in the southern part of the state, we have begun work with the school district to do a series of presentations on family involvement in the fall of 2017.

Our language access plan was developed over the summer of 2012 and finalized at the October 3, 2013 meeting of our Board of Directors.  Staff training on the language access plan occurred during the month of November 2012.  We provided refresher training to our staff in July, 2016.

The mission of our parent center is “to empower families and youth to individually and collectively advocate for improved functional and educational outcomes for children with disabilities.”

Our Board is comprised of 10 members, 7 of whom are parents of children with disabilities under the age of 26 years. Each is appointed to serve a three-year term; a second term is allowed. After two consecutive terms, a Board member must vacate the position for one year. Officers are elected by Board members from the membership. Current members of the Board of Directors include --

| Name | Role(s) | Parent of a CWD | Representing | Board role(s) | Board Term |
| --- | --- | --- | --- | --- | --- |
| Jane Smith | Parent, Gen Educator teacher (Secondary, Math) | 7 year old child with CP | Western part of state | *President | 1st term; ends 9/30/18 |
| Ann Doe | School administrator |  | Central part of state | *Vice President | 1st term; ends 9/30/18 |
| Jim Jones | Parent, Attorney | 21 year old child w ID | Northern region of state | *Secretary | 2nd term; ends 9/30/18 |
| Junior Dunlap | Parent, Vocational Rehab Specialist | 3 year old child with DD | Eastern region of state | *Chair of Finance | 1st term; ends 9/30/17 |
| Cindy Sunshine | Parent | 13 year old with Autism | State capital region Major city | Chair of Admin and Bylaws | 1st term; ends 9/30/18 |
| Cathy Jones | Parent, Individual with a Disability | 20 year child with LD | Eastern region of State; military families | Chair of Communications | 1st term; ends 9/30/18 |
| Sally Mane | Former State Director of SPED |  | Major cities | Member at large | 2nd term; ends 9/30/17 |
| Joe Schmoe | Fund raiser | 30-year old child w Autism | Southwestern region | Member at large | 2nd term; ends 9/30/17 |
| Barbara Holt | Gen education teacher; bilingual | 15 year old with Autism | BIA School; Native American families | Member at large | 1st term; ends 9/30/18 |
| Laura Homes | Parent, Real Estate agent, bilingual | 10 year old with LD (dyslexia) | Southern region of State | Member at large | 1st term; ends 9/30/19 |

NOTE: (*) Executive Committee member

# Text boxes

OMB No. 1894-0003

Exp. 02/28/2011

OMB No. 1875-0106

Exp. 06/30/2001

OMB No. 1875-0106

Exp. 06/30/2001

OMB No. 1894-0003

Exp. 02/28/2011

OMB No. 1875-0106

Exp. 06/30/2001

OMB No. 1875-0106

Exp. 06/30/2001

OMB No. 1894-0003

Exp. 02/28/2011

OMB No. 1875-0106

Exp. 06/30/2001

OMB No. 1875-0106

Exp. 06/30/2001